## Individual Timesheets for all s
Week | Student ID | Name | Hours [1- 6] | Activity details
Week 03 | S394695 | Amsh Shrestha | 1 | Research multiple issues faced by people on technological area
Week 03 | S394695 | Amsh Shrestha | 1 | Identified the most suitable candidate:splitsync
Week 03 | S394695 | Amsh Shrestha | 1 | Did analysis on alternatives/competitors, their strength and weakness
Week 03 | S394695 | Amsh Shrestha | 1 | Created canvas on how we will build the application and what will be different from competitors
Week 03 | S394695 | Amsh Shrestha | 0.5 | Held a meeting to present the idea to decide to progress, merge or discard the idea
Week 03 | S394695 | Amsh Shrestha | 0.5 | Finalised the project
Week 03 | S394695 | Amsh Shrestha | 0
Week 04 | S394695 | Amsh Shrestha | 0.5 | Updated trello about tasks to perform in week 04
Week 04 | S394695 | Amsh Shrestha | 1 | Designed SplitSync wireframe layouts: onboarding and balance dashboard
Week 04 | S394695 | Amsh Shrestha | 1 | Designed SplitSync wireframe layouts : bill setup and bill detail screens
Week 04 | S394695 | Amsh Shrestha | 1 | Designed SplitSync wireframe layouts: payment confirmation and notifications
Week 04 | S394695 | Amsh Shrestha | 0.5 | Created Kinde Account and Test Keys
Week 04 | S394695 | Amsh Shrestha | 0.5 | Scaffold PWA react and .net monorepos
Week 04 | S394695 | Amsh Shrestha
Week 05 | S394695 | Amsh Shrestha | 3 | Built authentication backend: ASP.NET Core Identity, JWT issuance, register/login by email or username, EF Core + SQLite migration
Week 05 | S394695 | Amsh Shrestha | 1.5 | Built homepage and profile pages in React frontend
Week 05 | S394695 | Amsh Shrestha | 1.5 | Resolved git rebase conflict merging authentication work with teammates' changes; verified build and tests passed
Week 06 | S394695 | Amsh Shrestha | 3 | Built group feature backend: Group + GroupMember models, GroupsController (create/list/add-member/join-by-ID endpoints), migration applied to Supabase
Week 06 | S394695 | Amsh Shrestha | 2 | Built GroupsPage frontend: create/list/join groups, per-group add-member form, wired to real API
Week 06 | S394695 | Amsh Shrestha | 0.5 | Removed unused Continue with Google sign-in stub from AuthenticationPage
Week 06 | S394695 | Amsh Shrestha | 0.5 | Git workflow troubleshooting: resolved commit message quoting issue
Week 07 | S394695 | Amsh Shrestha | 2 | Built expense-splitting backend logic: equal, unequal, and percentage split calculations
Week 07 | S394695 | Amsh Shrestha | 1.5 | Built settle-up balances backend logic and group management endpoints (rename, delete, leave, kick member, account deletion)
Week 07 | S394695 | Amsh Shrestha | 1.5 | Wired expense/split and settle-up frontend UI to the new API endpoints
Week 07 | S394695 | Amsh Shrestha | 1 | UI polish pass across group and expense screens
Week 08 | S394695 | Amsh Shrestha | 2.5 | Planned and implemented Group Dashboard restructuring: added /groups/:id routing, split GroupsPage into list-only view, built GroupDashboardPage with Overview/Transactions/Members tabs
Week 08 | S394695 | Amsh Shrestha | 1.5 | Built AddExpenseModal component (equal/unequal/percentage split as an overlay modal) and wired Transactions tab to merge expense + settlement history
Week 08 | S394695 | Amsh Shrestha | 1 | Verified dashboard end-to-end: clean TypeScript build and lint, full API smoke test (all split methods, balances, settlements, rename/remove member), ran client+server locally
Week 08 | S394695 | Amsh Shrestha | 0.5 | Git hygiene: added bin/obj to .gitignore, untracked SecureVault build artifacts causing spurious diffs on rebuild
Week 08 | S394695 | Amsh Shrestha | 0.5 | Merged amsh branch into main
Week 08 | S394695 | Amsh Shrestha | 2 | Built in-app notification feature backend: Notification model + migration, NotificationService, NotificationsController (list/unread-count/mark-read/mark-all-read), hooked into 5 mutation points across Groups/Expenses/Settlements controllers
Week 08 | S394695 | Amsh Shrestha | 2 | Built notification frontend: bell icon with unread badge + dropdown, first shared Header/AuthenticatedLayout in the app (introduced nested routing), verified all 4 trigger types plus the group-deletion cascade edge case via API smoke test
Week 08 | S394695 | Amsh Shrestha | 1.5 | Added edit/delete for expenses: PATCH/DELETE endpoints restricted to the paying member, refactored Create's validation into a shared ValidateAndComputeShares method reused by Update
Week 08 | S394695 | Amsh Shrestha | 1 | Reworked AddExpenseModal to handle create-or-edit in one component; added Edit/Delete buttons to the Transactions tab gated on ownership; verified via API smoke test (403 checks, balance updates, split-method change)
Week 08 | S394695 | Amsh Shrestha | 1 | Deployment planning for Render: walked through CORS, auto-migrate-on-boot, HTTPS-redirect-behind-a-proxy, and the client/API URL sequencing needed before Week09 deploy
Week 08 | S394695 | Amsh Shrestha | 0.5 | Updated Trello board: marked Notification feature and added/completed Edit/delete-expenses card to reflect actual progress
Week 08 | S394695 | Amsh Shrestha | 1.5 | Modernised the UI: added light/dark theme toggle, restyled the header, notification bell and all pages
Week 08 | S394695 | Amsh Shrestha | 1.5 | Added expense split suggestions: split amounts auto balance in AddExpenseModal, plus a member search endpoint for adding members to a group
Week 09 | S394695 | Amsh Shrestha | 1 | Made split auto balancing work for unequal ($) splits too, suggested values show in italics; added show/hide password button on the sign in page
Week 09 | S394695 | Amsh Shrestha | 0.5 | Fixed Biome lint and formatting issues in the client
Week 09 | S394695 | Amsh Shrestha | 2.5 | Built receipt photo backend: ExpenseReceipts table + migration, upload/view/remove endpoints (only the payer can upload, 5 MB limit, checks the file is really an image), 6 integration tests
Week 09 | S394695 | Amsh Shrestha | 1.5 | Built receipt photo frontend: attach/replace/remove with preview in AddExpenseModal, photos compressed before upload, receipt viewer on the Transactions tab
Week 09 | S394695 | Amsh Shrestha | 1 | Fixed local errors after the new migration: applied it to our Supabase database and fixed the empty migration history so dotnet ef database update works again
Week 09 | S394695 | Amsh Shrestha | 1 | Added auto refresh to the group dashboard (every 20 seconds and when you come back to the tab), fixed old error messages staying on screen
Week 09 | S394695 | Amsh Shrestha | 1 | Updated project documentation: README, data dictionary (receipts table) and my Project Documentation
Week 09 | S394695 | Amsh Shrestha | 0.5 | Updated Trello board and merged amsh branch into main (PR #9)
Week 10 | S394695 | Amsh Shrestha | 1.5 | Added a Usage Analytics (Tableau) section to Project Documentation: embedded all 9 charts from week10/charts with captions, flagged which ones model SRS features that aren't built yet
Week 10 | S394695 | Amsh Shrestha | 1 | Added a Conclusion section tying the build back to the Aim/Objectives and naming what's left before submission
Week 10 | S394695 | Amsh Shrestha | 1.5 | Built a CDU-branded cover page for the report: generated the design, inserted it as a true full-bleed first page in its own zero-margin section so the rest of the formatting didn't shift
Week 10 | S394695 | Amsh Shrestha | 2.5 | Built SplitSync_Presentation.pptx from scratch: 15-slide widescreen deck covering intro, aim/objectives, scope, architecture, features, testing, known gaps, usage analytics and conclusion
Week 10 | S394695 | Amsh Shrestha | 0.5 | Moved Project_Documentation.docx and SplitSync_Presentation.pptx into the shared Documentation folder so the team can open them
Week 10 | S394695 | Amsh Shrestha | 0.5 | Updated Trello board to reflect the finished report and presentation